## 10_31_13
Meeting Leader: | John
Meeting Scribe: | Albert
Agenda |  | Desired Outcomes
Milestone 1
Milestone 1 Questions |  | Gain clarity on the assignment
What is "Add time dimension (e.g., when to use existing readings)"? |  | Adding date widget and calling "GET SENSOR READINGS IN A TIME RANGE FOR A DEVICE"
Templates for the deliverables?
2 teams are working on Project 4 - are the focuses going to be different?
Integrate with visualization; add visualization of sensor health (Dashboard) |  | Configurable sensor monitoring - How to Monitor the sensors (team 1: doing heatmap - don't need to do this.) . Do a dashboard - want to know which sensors are wrong, from that info - find out where it is, then can do some debugging (check firmware). Need to decide which one sensors are faulty. Up to us how we decide. e.g. if we haven't seen a reading in the past minute. | Figure out a way to meet w/ NASA PM
Geofence - Location Awareness |  | Our job to create geofence algorithm and provide it to Joe's team. Create a blackbox API for Joe. | (good for a part-time team to work on this)
Virtual sensor serialization to Json/XML |  | Joe's project needs to serialize, and store into local file. Joe's team does JSON. We (our team) can store in XML (for use in Formal Verification and other purposes). Need to design a XML schema. Virtual sensor editor needs to read it in and display it to the browswer. | Get code from Joe - Visualization Code - dashboard (enhance it and possibly add alerts - he already has a list of good sensors, bad sensors), heatmap. Check why Visualization piece is not working at the moment. | Design needs to be adaptable to bigger/future projects
Add to VSE some kind of control structure |  | E.g. a loop. Virtual sensors have data - they act as data processors (inputs/outputs). Not too different than a procedure. There exists multi-step procedures for processing sensor data (business process). This task is to add control flows to this. E.g. If we want 80 sensors to be displayed, we don't want to have to drag 80 sensors onto the page. | Proof of concept!
Class ends on Dec. 12th

## 11_7_13
Meeting Leader: | Mari
Meeting Scribe: | John
Agenda |  | Desired Outcomes
Milestone 2
Milestone 2 Questions |  | Gain clarity on the assignment
Einstein API does not return other gateway information, is this expected? |  | Jeenet_1 gateway crashed, SweetFeedback project on hold. NASA is in flux as well.
Einstein API does not return sensors that are available for device in one call. |  | Expected, send email to Bo for requests.
Einstein API returns device ids that are not there in getDevices(). |  | Design last year did not support mobile devices. Data model needs to be changed fundamentally. Data is not consistent.
Which team is working on the current APIs? |  | Bo Liu, Team 2.
What's the reason for using XML? |  | Eventually be able to use virtual sensor data (as xml) with http://taverna.org.uk. XSD. Have API that just returns XML or stores it? Just return XML is fine, need to work with Team 2.
JSON to XML? |  | Joe's team will work with storing the JSON, maybe using node.js. Joe's JSON is based on our schema. Our team can write standalone java program, input is JSON of Virtual Sensor, output is XML. Work out a XML based language for Virtual Sensor using XSLT.